## Read me
The Draw Ledger
Stated versus actual, and claims versus evidence, in one file.
WHAT THIS IS
After approval, the record goes quiet. This workbook keeps it open: the facility's stated draw sits next to its actual draw, and every benefit claim sits next to the evidence that would show it was kept. An approval is not the end of assessment.
TWO MODES
Single facility: work in the Monthly actuals, Claims and Conditions tabs. Portfolio: the Portfolio tab assembles one row per facility on a shared municipal system, because no public process assembles that column, and a table somebody maintains is how that starts.
BASIS DISCIPLINE
Contracted capacity, application figures and press announcements are different numbers. Tag every stated figure with its basis and never sum across bases. The Stated baseline tab enforces this.
MAINTAINED BY
Built on the Sociable Systems post-approval monitoring framework. The maintained version of this workbook is a module deliverable: sociable.systems
STATUS LEGEND
Claims register · Status
verified | Evidence checked and holds.
partial | Holds in part, short of the promise.
deferred | Kept, moved, with a new date.
missed | Promised date passed, not kept or not evidenced.
not yet due | The promised date has not been reached.
Conditions register · Status
open | Due date not reached, nothing owed yet.
met | Met, evidence on file.
past due | Due date passed.
closed | Closed out by the instrument or the process.
Stated baseline · Basis (never sum across bases)
contracted · application · announcement · licence condition · measured | Different numbers from different documents; n/a where nothing is stated.
Claims register · Instrument
condition of consent · agreement | Bindable: a condition of consent or a signed instrument.
marketing · none | An unenforceable benefit is a forecast. Forecasts do not bind.
Conventions: n/a marks a cell empty by design, never a bare dash. Dropdown cells stay blank until a value is chosen. EXAMPLE rows are tinted like the seeds on each register and are deletable: delete them to start your own file. If you delete them, repoint the band formulas on the Stated baseline tab; the Dashboard and the Monthly actuals read the band from that row.

## Dashboard
Dashboard
STATED ANNUAL ELECTRICITY | LATEST MONTH ACTUAL | VARIANCE VS STATED BAND |  |  | CONDITIONS PAST DUE
|  | latest month against the stated monthly band (band ±10%) |  |  | due date passed and status not closed
CLAIMS VERIFIED | CLAIMS PARTIAL | CLAIMS DEFERRED |  |  | CLAIMS MISSED
evidence checked and holds | holds in part, short of the promise | kept, moved, with a date |  |  | promised date passed: not kept or not evidenced
WATER YTD (Ml) | DIESEL YTD (L) | PERMANENT JOBS: LATEST ACTUAL |  |  | CUMULATIVE DRAW ASSESSED ANYWHERE
0 MVA
sum of the Monthly actuals water column, m³ converted to Ml | litres, Monthly actuals sum; the generator month shows in the notes |  |  |  | Not an error. No public process assembles it; the Portfolio tab is where that starts.
teal line: monthly actual · dashed rust: the stated monthly band, floor and ceiling (annual / 12, ±10%) · gaps are months not yet reported
Chart feed: do not delete; the bar chart reads these cells.
|  |  | Status | Claims (count)
verified
partial
deferred
missed
not yet due

## Stated baseline
Stated baseline
One row per stated figure, each tagged with its basis: contracted, application, announcement, licence condition, measured. Never sum across bases. EXAMPLE rows are tinted; delete them to use the register, then repoint the band formulas on the electricity row.
Item | Stated value | Unit | Basis | Source document | Location (section, page) | Date entered | Note | Monthly band midline (kWh) | Monthly band floor (kWh) | Monthly band ceiling (kWh)
Connection size | 120 | MVA | application | Application: electrical annexure (EXAMPLE) | s.4.2, p.12 | 2026-01-15 | As applied for, not as contracted; confirm against the connection agreement. | n/a | n/a | n/a
Annual facility electricity | 1090 | GWh/yr | application | Application: energy annexure (EXAMPLE) | s.5.1, p.18 | 2026-01-15 | 120 MW IT at 80% utilisation, PUE 1.3.
Water, evaporative case | 1,500 to 3,400 | Ml/yr | announcement | Published industry range (EXAMPLE) | n/a | 2025-11-02 | Published range 1.8 to 4.0 L/kWh of IT energy; design not stated; the spread is the finding. | n/a | n/a | n/a
Cooling design | n/a (not stated) | n/a | n/a | n/a | n/a | 2025-11-02 | The spread is the finding. | n/a | n/a | n/a
Permanent jobs | 60 | roles | announcement | Media announcement (EXAMPLE) | n/a | 2025-11-02 | Tracked against actual headcount in Claims register (CL-01). | n/a | n/a | n/a
Noise at boundary | 42 | dB(A) day | application | Application: acoustic annexure (EXAMPLE) | s.7.3, p.31 | 2026-01-15 | Modelled; checked monthly in Monthly actuals. | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Band columns: the stated annual electricity divided by 12, ±10%, in kWh. They feed the Dashboard band and the Monthly actuals variance, and they belong to the application-basis electricity figure; never sum across bases.

## Monthly actuals
Monthly actuals
Start month (edit) | 2025-07-01 | month labels follow this date; months 1 to 12 are example data (EXAMPLE) |  |  |  |  | Promised local share %, from Claims register (CL-02) |  |  |  |  | drives the local headcount flag |  | Chart feed (24 months): #N/A marks a month not yet reported; the Dashboard line chart reads these columns.
Month | Electricity (kWh) | Peak demand (kVA) | Water (m³) | Diesel (L) | Generator hours | Noise dB(A) day | Noise dB(A) night | Permanent headcount | Local headcount | Local procurement (R) | Variance vs stated band % | Note | Exception flag | Chart feed: month | Actual (kWh) | Band floor (kWh) | Band ceiling (kWh)
| 89400000 | 96500 | 138500 | 0 | 0 | 41.2 | 39.8 | 12 | 4 | 182000 |  | n/a
| 90150000 | 97200 | 141200 | 0 | 0 | 41.5 | 40.1 | 15 | 5 | 205000 |  | n/a
| 91800000 | 98400 | 139800 | 0 | 0 | 40.9 | 39.6 | 19 | 7 | 248000 |  | n/a
| 92600000 | 99100 | 144600 | 0 | 0 | 41.6 | 40.2 | 24 | 9 | 310000 |  | n/a
| 93600000 | 100300 | 149300 | 0 | 0 | 41.3 | 39.9 | 28 | 11 | 385000 |  | n/a
| 94900000 | 101100 | 152100 | 0 | 0 | 41.8 | 40.4 | 31 | 12 | 462000 |  | n/a
| 95700000 | 102000 | 156800 | 0 | 0 | 41.1 | 39.7 | 34 | 14 | 548000 |  | n/a
| 96400000 | 102600 | 158400 | 0 | 0 | 41.7 | 40.3 | 37 | 15 | 663000 |  | n/a
| 97300000 | 103500 | 161900 | 3100 | 14 | 41.9 | 40.5 | 39 | 16 | 782000 |  | Grid constraint: generators ran 14 hours (EXAMPLE)
| 98100000 | 104200 | 164700 | 0 | 0 | 41.4 | 40 | 41 | 17 | 917000 |  | n/a
| 98600000 | 104900 | 168300 | 0 | 0 | 41.6 | 40.2 | 43 | 17 | 1064000 |  | n/a
| 99000000 | 105400 | 171600 | 0 | 0 | 41.8 | 40.4 | 44 | 18 | 1239000 |  | n/a
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported
| n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | not yet reported

## Claims register
Claims register
One row per benefit claim, quoted verbatim from its source. Instrument = marketing or none means nothing binds it: an unenforceable benefit is a forecast. EXAMPLE rows are tinted; delete them to use the register.
Claim ID | Claim (verbatim from the source) | Promised figure | Unit | Promised by (date) | Instrument | Evidence that would count | Evidence reference | Status | Date checked | Checked by | Note | Exception flag
CL-01 | 60 permanent roles within 12 months of full commissioning | 60 | roles | 2026-06-30 | condition of consent | Monthly payroll headcount at the facility, with role descriptions | EXAMPLE: payroll extract, 2026-06 | partial | 2026-07-15 | EAP (EXAMPLE) | 44 roles at month 12; the ramp is still short of the promise.
CL-02 | 40% local procurement of non-capital spend by year 3 | 40 | % of non-capital spend | 2028-06-30 | marketing | Audited procurement ledger split by supplier address | n/a | not yet due | n/a | n/a | Marketing claim with no instrument behind it.
CL-03 | Cooling water drawn from treated effluent, not potable | n/a | n/a | 2026-03-31 | condition of consent | Water supply agreement plus metering: effluent volume against potable volume | EXAMPLE: no agreement located yet | deferred | 2026-07-15 | EAP (EXAMPLE) | Effluent scheme delayed; potable supply in use while commissioning continues.
CL-04 | Noise at the boundary maintained within 42 dB(A) | 42 | dB(A) day | 2026-06-30 | condition of consent | Boundary acoustic monitoring, day and night, monthly | EXAMPLE: Monthly actuals, noise columns | verified | 2026-07-15 | EAP (EXAMPLE) | Twelve months within 42 dB(A) day.
CL-05 | Skills programme for 12 local learners annually | 12 | learners/yr | 2026-06-30 | none | Training provider enrolment records, learners from the local ward | n/a | missed | 2026-07-15 | Monitoring panel (EXAMPLE) | No programme exists. No instrument holds this promise: it binds no one.
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a |  | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a |  | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a |  | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a |  | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a |  | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a |  | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a |  | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a |  | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a |  | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a |  | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a |  | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a |  | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a |  | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a |  | n/a | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a |  | n/a | n/a | n/a
Formulas:
Exception flag = IF(OR([Status]="missed",AND([Status]="deferred",ISNUMBER([Promised by (date)]),[Promised by (date)]<TODAY())),ROW()-5,"")

## Conditions register
Conditions register
One row per condition attached to an instrument: consent, licence or agreement. A condition with a due date in the past and no closure is the exception report's third list. EXAMPLE rows are tinted; delete them to use the register.
Condition # | Instrument | Requirement (paraphrase) | Due date | Owner | Status | Evidence reference | Note | Exception flag
RC-01 | Environmental authorisation | Annual environmental audit report to the competent authority | 2026-03-31 | EAP | past due | n/a | The audit window closed with no submission on record.
RC-02 | Water use licence | Quarterly groundwater sampling and laboratory reports | 2026-09-30 | EAP | open | EXAMPLE: second-quarter sample in file | n/a
RC-03 | Noise condition | Post-commissioning acoustic verification report | 2026-06-30 | Acoustic consultant | met | EXAMPLE: report 2026-06; twelve months within 42 dB(A) day | Feeds Claims register CL-04.
RC-04 | Site access condition | Transport management plan annual review | 2027-01-31 | Facility manager | open | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  | n/a | n/a
Formulas:
Exception flag = IF(OR([Status]="past due",AND(ISNUMBER([Due date]),[Due date]<TODAY(),[Status]="open")),ROW()-5,"")

## Exception report
Exception report
Facility name (edit) |  | Facility A (EXAMPLE) |  | As at
1 · Stated vs actual beyond tolerance (beyond ±25% of the stated monthly band)
Month | Electricity (kWh) | Variance | Note
2 · Claims not kept or not evidenced
Claim ID | Claim |  |  | Promised by | Status
3 · Conditions past due
Condition # | Instrument | Requirement |  |  |  | Due date
Where the answer is that the process does not require it, that is the mechanism named in the applicant's own words. Approval is not the end of assessment.

## Portfolio
Portfolio (municipal mode)
Facilities on this system: |  |  |  | System headroom (MVA): |  | 300
Assessed cumulatively:
if the second number is zero, that is the finding, and it is the expected one.
Facility (name or erf) | Basis of load figure | Contracted draw (MVA) | Stated annual electricity (GWh) | Stated water (Ml/yr) | Cooling design stated? | Cumulative assessment exists? | Post-approval figures reported? | Source | Note
Facility A | application | 120 | 1090 | 2400 | yes | no | yes | EXAMPLE: application annexures | n/a
Facility B | application | 85 | 720 | 1550 | yes | no | no | EXAMPLE: application annexures | Post-approval figures not yet reported.
Facility C | application | 60 | 480 | n/a (not stated) | no | no | no | EXAMPLE: application annexures | Cooling design not stated: the spread is the finding.
Facility D | contracted | 45 | n/a (not stated) | n/a (not stated) | n/a | unknown | not yet | EXAMPLE: utility connection agreement | Connection agreement only; no application figures published.
Facility E | announcement | 90 | 850 | 1300 | yes | unknown | not yet | EXAMPLE: press announcement | announcement basis: do not sum; shown for the exception report
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
n/a | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a
Total (excludes announcement basis)
The total no public process assembles. Maintained here because nobody else keeps it.