## Risk Register
Risk ID | Source grievance | Category | Severity | Status | Days open | Treatment / Resolution | Owner | PS hook | Notes
R-001 | G-015 | GBVH | Critical | Escalated | 59 | Independent investigator engaged; site HR director briefed. | [assign] | PS2 | Outside main log per protocol; placeholder.
R-002 | G-014 | Health & safety | High | Investigating | 44 | Air-quality monitoring deployed; clinic outreach scheduled. | [assign] | PS1, PS3, PS4 | Open — cross-linked pattern with G-013.
R-003 | G-006 | GBVH | High | Investigating | 28 | Supervisor suspended pending investigation; specialist GBVH protocol activated. | [assign] | PS2, PS4 | Handled outside main log per GBVH protocol confidentiality; placeholder only.
R-004 | G-016 | Procedural | High | Investigating | 24 | Engagement records audit underway; contractor liaison briefed. | [assign] | PS1 | Whistle-blower channel — handle with elevated confidentiality.
R-005 | G-002 | Environment | High | Investigating | 8 | Independent water sampling commissioned; interim work-method statement revised. | [assign] | PS1, PS3, PS6 | Caller anonymous. Severity flagged by AI but confirmed by social lead.
R-006 | G-020 | In-migration | Medium | Investigating | 86 | In-migration management plan being updated; municipal coordination meeting held. | [assign] | PS1, PS4 | Long-running — open >60 days, escalation candidate.
R-007 | G-011 | Workforce | Medium | Resolved | 39 | Accommodation audit; additional units commissioned. | [assign] | PS2
R-008 | G-013 | Health & safety | Medium | Resolved | 20 | Water-spray suppression deployed; complaint review at next CLO meeting. | [assign] | PS1, PS3, PS4 | Pattern-flagged.
R-009 | G-001 | Livelihoods | Medium | Resolved | 25 | Compensation under livelihood restoration framework — boat repair + 14 days lost-income. | [assign] | PS1, PS5 | Cross-ref engagement E-001.
R-010 | G-004 | Workforce | Medium | Resolved | 7 | Payroll fix; one-off interest payment; payroll cycle audit ordered. | [assign] | PS2 | Recurring pattern — see audit finding A-12.
R-011 | G-005 | Environment | Medium | Investigating | 4 | CIA addendum drafted; review meeting scheduled 15 June. | [assign] | PS1, PS6 | Procedural complaint, not project-affected community — log separately for analytics.
R-012 | G-012 | Local content | Low | Resolved | 23 | Procurement plan revised; quarterly local-content reporting added. | [assign] | PS1
R-013 | G-019 | Workforce | Low | Received | 11 | Awaiting acknowledgement — SLA window still open. | [assign] | PS2 | New — illustrates pending case.