# Stakeholder Profile — Affected Community — Macuse Village

ID S-001  ·  Community  ·  Zambezia, MZ

Generated: 2026-05-26 13:52  ·  Sociable Systems engagement tracker  ·  sociable.systems

# Profile

| Type | Community |
| --- | --- |
| Sub-group | Resettlement Zone 1 |
| Geography | Zambezia, MZ |
| Influence | High |
| Interest | High |
| Vulnerability flag | Yes |
| Key concerns | Land access, resettlement compensation, fishing rights |
| Engagement lead | T. Mbeki |
| Last contact | 2026-05-12 |
| Next planned contact | 2026-06-02 |
| IFC PS hook | PS1, PS5 |
| Notes | Customary tenure not titled; matrilineal land inheritance — engage women's group first. |

# Engagement history (3 entries)

| Date | Mode | Topic | Commitments | Owner | Status |
| --- | --- | --- | --- | --- | --- |
| 2026-04-02 | Public hearing | Compensation framework presentation | Convene 3 focus groups by end of April | T. Mbeki | Closed |
| 2026-05-12 | In-person meeting | Resettlement Zone 1 walkthrough | Provide draft Resettlement Action Plan in Portuguese by 30 May | T. Mbeki | Open |
| 2026-05-18 | GrieVoice call | Multilingual intake — community phoned in concern | Investigate water turbidity downstream of works (see G-002) | T. Mbeki | Open |

# Linked grievances (1)

| ID | Received | Category | Severity | Status | Closed |
| --- | --- | --- | --- | --- | --- |
| G-002 | 2026-05-18 | Environment | High | Investigating |  |

# Open commitments (2)

• [Open] Provide draft Resettlement Action Plan in Portuguese by 30 May — due 2026-05-30 (owner: T. Mbeki)

• [Open] Investigate water turbidity downstream of works (see G-002) — due 2026-05-25 (owner: T. Mbeki)

# Engagement summary

[AI-DRAFT, NEEDS PRACTITIONER REVIEW] Affected Community — Macuse Village is a community stakeholder with High influence and High interest. To date there have been 3 formal engagements and 1 linked grievances. [Add: relationship dynamics, sensitivities, recommended approach for handover.]